## Sheet1
Hidden Falls Regional Park Trails and Open Space Expansion Project - Timeline
Date | Activity
2020-11-17 | Anticipated Board of Supervisors decision on Final SEIR and Conditional Use Permit Modification for the Project
Dec/Jan -20/21 | Award of grant
Dec/Jan -20/21 | Subsequent to certification of the Final SEIR and approval of the CUP Modification by the Board, and award of funds, County will begin applying for state and federal permits and will prepare construction documents for bidding
By end of 2021 | Award of construction contract by Board of Supervisors
Spring/Summer 2022 | Begin construction
2022-11-01 | Complete Construction
Winter 22/23 | Project Closeout